## Slide 1: Report on ‘DeltaCode’ Project Management Presentation
To be Presented by Zain Khalid (FA19-BCS-112) & Zohaib Mehmood (FA19-BCS-087)

## Slide 2: Project analysis slide 2
Report’s Content
1. Project Description
2. Report Method
3. Initiation
4. Planning
5. Budgeting
6. Changings
DeltaCode PROJECT

## Slide 3: Project analysis slide 3
Project Description
“As part of Acceleron Corp.’s mission to solve intelligence, we want you to develop a system called “DeltaCode” that writes computer programs at a competitive level.”

## Slide 4: Project analysis slide 3
Report Methodology
This report strictly adhere to the methodology instructed through the example 3.11 and chapter 3 of “Introduction to software project management” by Adolfo Villafiorita.

## Slide 5: Project analysis slide 3
Report Methodology
Initiating
Building a Plan
Creating a Budget for the Project
Changing the plan to meet external Deadline
Title
Scope Document
Identify Team Requirements
Obtain Authorization
Development Model
Gant Chart
Deliverables from the Client
Cost of Resources
Budget Estimation for the Project
Changing the project approach
Reducing or changing the project scope
Allocating resources more efficiently
Fast tracking.

## Slide 6: Project analysis slide 3
Initiating
Title : DeltaCode
Scope Document

## Slide 7: Project analysis slide 3
Initiating
Scope Document
Major Stake Holders
Zed Developers
Acceleron Corps

## Slide 8: Project analysis slide 3
Initiating
Scope Document
Goals
Experimental Application.
Deep Learning Algorithm.
Competitive Code Output.

## Slide 9: Project analysis slide 3
Initiating
Scope Document
Total Budget
100,000$

## Slide 10: Project analysis slide 3
Initiating
Scope Document
Project TimeLine
Begin : 22– June – 2022
Deliver by : 8-July-2023

## Slide 11: Project analysis slide 3
Initiating
Scope Document
Deliverables
Scope Document
Project Plan (Gantt Chart)
Budget Distribution List
Progress Report
Test Reports

## Slide 12: Project analysis slide 3
Initiating
Scope Document
Constraints
Hyper Complexity.
Processing Power Limitation.
Difficulty In recognizing intent of Statements.

## Slide 13: Project analysis slide 3
Initiating
Scope Document
Risks
Crashing due to buffer overload.
Miss-identification of Variables.
Input not identifiable.
Limitation of algorithm.

## Slide 14: Project analysis slide 3
Initiating
Requirements of the development team
TPU enabled Work Station
Deep Learning Concepts
Algorithm Design Concepts
NLP Expert

## Slide 15: Project analysis slide 3
Initiating
Requirements of the development team
Request for Project Manager : Allah Deta
Request has been granted by the performing organization body.

## Slide 16: Project analysis slide 3
Initiating
Authorization:
In light of the scope document,
The Client “Acceleron Corps.” has authorized to began work.
The performing organization “Zed Developers” has authorized to began work.

## Slide 17: Project analysis slide 3
Building a Plan
Development Model
Water Fall

## Slide 18: Project analysis slide 3
Building a Plan
For the whole lifetime of the project;
It has been divided into 4 work packages.
WP1. Inception
WP2. Construction
WP3. Deployment
WP4. Experimentation

## Slide 19: Project analysis slide 3
Building a Plan
Work Breakdown Structure

## Slide 20: Project analysis slide 3
Building a Plan
Gantt Chart

## Slide 21: Project analysis slide 3
Building a Plan
Gantt Chart

## Slide 22: Project analysis slide 3
Building a Plan
Deliverable from Client
List of candidates for WP4
Acquisition Head
Adolf Hitler
IT Advisor
John Wick

## Slide 23: Project analysis slide 3
Creating a Budget
Cost of Resources
Budget Estimation

## Slide 24: Project analysis slide 3
Creating a Budget
Name | Type | Maximum Availability % | Cost ($/h) | Overtime ($/h) | Accrue
R1. Requirement Specialist | Work | 100% | 40 | 60 | Prorated
R2. System Architect | Work | 100% | 40 | 60 | Prorated
R3. Developer | Work | 100% | 40 | 60 | Prorated
R4. Developer | Work | 100% | 40 | 60 | Prorated
R5. NLP Expert | Work | 100% | 40 | 60 | Prorated
R6. Tester | Work | 100% | 50 | 100 | Prorated
PM. Project Manager | Work | 100% | 60 | 100 | Prorated
R7. Researcher | Advice | 100% | 60 | 100 | Prorated
R8. TPUs | Equipment | 100% | 25 | 50 | Prorated
Cost of Resources

## Slide 25: Project analysis slide 3
Creating a Budget
Task Name | Resource Name | Work ( Days) | Cost
Project |  | 445 | 70,000$
Inception |  | 120 | 10,000$
Requirements Definition | R1. Requirements Specialist | 20 | 2000$
Design (API) | R2. System Architect | 10 | 4000$
Concept Preparation | R7. Designer | 30 | 1000$
Design Validation | R1. Requirements Specialist | 20 | 1000$
System Specifications | R2. System Architect | 40 | 2000%
Construction |  | 250 | 40,000$
Text Parser | R3. Developer | 10 | 8000$
Variable Identifier | R3. Developer | 20 | 2000$
Dependence Engine | R3. Developer | 50 | 4000$
Conceptualizer | R4. Developer | 30 | 5000$
Budget Estimation

## Slide 26: Project analysis slide 3
Creating a Budget
Task Name | Resource Name | Work (IN Days) | Cost
Algorithm Design | R4. NLP Expert | 8 | 1000$
Neural Engine | R4. Developer | 30 | 10,000$
Interface Engine | R5. Developer | 10 | 7000$
.NET Desktop Adaptation | R7. Developer | 15 | 3000$
Deployment in Testing Env | R3. Developer | 2 | 500$
Design Validation |  | 15 | 200$
System Ready for Testing |  | 5 | 50$
Test Case Definition | R6. Tester | 2 | 1000$
Test Cases | R6. Tester | 3 | 1500$
System Testing | R6. Tester | 6 | 1000$
System Fixing | R3. Developer | 3 | 2400$
System Ready for Deployment |  | 1 | 50$

## Slide 27: Project analysis slide 3
Creating a Budget
Task | Resource Allocation | Work (In Days) | Cost
Deployment |  | 75 | 20,000$
System Installation | R2. Developer | 5 | 2000$
System Ready for Experimentation |  | 1 | 500$
Experimentation | R7. Developer | 50 | 2000$
Candidates for Test |  | 4 | 7000$
Experimentation |  | 10 | 1000$
Corrective Maintenance | R5. Developer | 6 | 500$
Project Management | PM Project Manager | 4 | 1500%

## Slide 28: Project analysis slide 3
Changing plan to meet deadline
For the given plan we are 1 month late.

## Slide 29: Project analysis slide 3
Changing plan to meet deadline
To meet deadline we have 2 options
Changing the Project Approach
Fast Tracking

## Slide 30: Project analysis slide 3
Changing plan to meet deadline
We have decided to Change the Project Approach
Make three contracts
Initiation
Construction
Deployment and Experimentation

## Slide 31: Project analysis slide 3
Changing plan to meet deadline
We have decided to Change the Project Approach
Parallel Model of Development

## Slide 32: Project analysis slide 3
Changing plan to meet deadline
Fast Tracking
Start Testing each module in construction package after it’s completion.

## Slide 33: Thank You
Presented by Zain Khalid (FA19-BCS-112) and Zohaib Mehmood (FA19-BCS-087)